Anthropic Deep Competency Program — Investment Case

Vamsi Duvvuri

June 4, 2026

# Executive Investment Memo: Anthropic Deep Competency Program

Date: June 4, 2026

Prepared by: Vamsi Duvvuri

Classification: Internal — Executive Leadership

## Executive Summary

Our clients are adopting Anthropic's Claude platform at an accelerating pace. When they select Anthropic, they need implementation partners who are not just familiar with the technology, but are certified, hands-on experts who have built real systems with it. Today, we lack that depth.

This memo proposes a $290,525 investment to build a deep Anthropic competency bench through an immersive 2-week training cohort in New York City. By mid-July 2026, we will have 12 certified Claude Architects across six roles, 2-3 qualified internal trainers, and a proven, repeatable enablement model that scales to other geographies — starting with India — without additional program design investment.

The real cash outlay is ~$38K. The remaining ~$253K is people's time that we are redirecting from client work to build a certified bench that generates revenue on Anthropic engagements for years.

This is not a vendor partnership or reseller play. This is about ensuring that when a client has already chosen Anthropic, our team shows up as the most credible delivery partner in the room.

## Strategic Context

### Market Landscape

Anthropic has emerged as a leading frontier AI company, with Claude models consistently ranking at the top of coding, reasoning, and long-context benchmarks. Enterprise adoption is accelerating across financial services, healthcare, technology, and professional services. Key market dynamics:

Agentic AI is becoming mainstream. Anthropic's Claude Code and Agent SDK position it as a leader in the shift from conversational AI to autonomous, tool-using agents. Clients are moving from experimentation to production deployments.

Enterprise governance requirements are increasing. Anthropic's Constitutional AI methodology and safety-first positioning (SOC 2, HIPAA eligible) make it a preferred choice for regulated industries — exactly our client base.

Multi-model strategies are standard. Clients are not choosing one AI vendor. They are building portfolios. Anthropic is increasingly the primary choice for reasoning-heavy, code-intensive, and long-context workloads, complemented by other providers for image/video generation and ecosystem-specific integrations.

Context window leadership. Claude's 1M token context window enables use cases (full-codebase analysis, large document processing, complex multi-step reasoning) that competitors cannot match at comparable quality.

### Organizational Need

We are a consulting firm. Our value proposition is expertise. When a client selects Anthropic and needs an implementation partner, they are evaluating us against:

Anthropic's own professional services team

Boutique AI consultancies with deep Claude specialization

Competitors who have already invested in Claude-specific training

Today, our Anthropic capabilities are broad but shallow — awareness-level, not delivery-level. We need practitioners who have:

Built production systems with the Claude API, not just run demos

Used Claude Code daily as part of their engineering workflow

Passed the Claude Certified Architect exam, providing external validation of their expertise

Followed a structured AI product process that can be replicated across client engagements

### Why Anthropic

This investment is not about picking a winner in the AI platform race. It is about responding to a market reality: clients are selecting Anthropic, and we need to be ready to deliver.

Anthropic's technology stack is particularly relevant to our practice because:

Claude API — The Messages API with tool use, vision, extended thinking, and prompt caching covers the full spectrum of enterprise AI use cases our clients pursue

Claude Code — The agentic CLI for software engineering is transforming how development teams work. Clients adopting it need partners who use it natively, not partners who read about it

Agent SDK — As clients move from single-model applications to multi-agent systems, we need architects who have built with the Agent SDK, not just evaluated it

Certification — The Claude Certified Architect credential provides a verifiable, third-party signal to clients that our people have deep, validated expertise

## Investment Proposal

### Program Scope

An immersive, 2-week training program in New York City, producing 12 certified Claude Architects and 2-3 qualified internal trainers through a "train the trainer" model. Week 1 is fully in-person; Week 2 is virtual.

US Cohort — New York City (2 weeks)

12 participants across six roles: Data Engineer, AI Engineer, Architect, Software Engineer, Business Analyst/Consultant, Product Manager (2 per role)

3 facilitators: PPMD (oversight, 8 hrs/week), Sr. Manager (full-time), Manager (full-time)

Intermediate-to-advanced practitioners

6 participants travel to NYC for Week 1; remaining 6 are local

2-3 participants selected as future co-facilitators for India and other geos

Purpose: Build the enablement machine — test curriculum, generate playbooks, produce trainers

Training Design — Two Integrated Tracks:

|-------|-------|-------------|

| Track | Focus | Requirement |
| --- | --- | --- |
| Certification Track | Systematic coverage of all Claude Certified Architect exam domains | Schedule and pass exam within 2 weeks of course completion. Exam fee reimbursed upon passing. |
| Build Track | AI product process — specs, harnesses, team collaboration — to build a real product | Full project from strategy to deployment to communications |

Daily Structure:

Monday: 11:00 AM – 4:00 PM (4 hrs structured)

Tuesday–Thursday: 8:00 AM – 5:00 PM (8 hrs structured, including breakfast brainstorming 8-9)

Friday: 9:00 AM – 3:00 PM (5 hrs structured, early release for travel)

Team dinners Monday and Thursday evenings

Evenings: self-directed work on ideas, assets, and builds

66 structured hours across 10 days, plus breakfast brainstorming and evening collaboration

Week 1 is technology-specific (Anthropic / certification-focused) — this portion is rebuilt per vendor for future cohorts. Week 2 is the AI Build Methodology — vendor-agnostic and fully reusable across all future Forge programs (OpenAI, NVIDIA, GCP, AWS, etc.).

Certification Exam Domains Covered (Week 1):

|--------|--------|-------------|

| Domain | Weight | Focus Areas |
| --- | --- | --- |
| Agentic Architecture & Orchestration | 25-27% | Agentic loops, multi-agent coordination, subagent spawning, task decomposition, session state, hooks |
| Claude Code Configuration & Workflows | 20% | CLAUDE.md hierarchy, path-scoped rules, custom skills, plan mode, CI/CD integration, batch processing |
| Prompt Engineering & Structured Output | 20% | Few-shot prompting, JSON schema design, validation-retry loops, multi-pass review, tool use for structured output |
| Tool Design & MCP Integration | 18-20% | Tool descriptions, structured error responses, tool distribution, MCP configuration, built-in tools |
| Context Management & Reliability | 15% | Cross-conversation persistence, summarization risks, error propagation, escalation patterns, information provenance |

### Detailed Day-by-Day Schedule

#### Week 1: Anthropic Technology Deep Dive & Certification (In-Person, NYC)

Monday — Foundations

|------|----------|

| Time | Activity |
| --- | --- |
| 11:00–12:00 | Welcome, program overview, team introductions, objectives |
| 12:00–1:00 | Lunch |
| 1:00–4:00 | Claude Foundations: models, API, Messages API, authentication, SDKs. Hands-on: first API calls, explore Claude.ai and Claude Code |
| Evening | **Team dinner.** Form build teams, brainstorm project ideas |

Tuesday — Prompt Engineering + Tool Design

|------|----------|

| Time | Activity |
| --- | --- |
| 8:00–9:00 | Breakfast + brainstorming: what would you build with Claude? |
| 9:00–12:00 | Prompt Engineering & Structured Output (Domain 4, 20%): explicit instruction criteria, few-shot prompting, JSON schema design, validation-retry loops, multi-pass review architectures |
| 12:00–1:00 | Lunch |
| 1:00–5:00 | Tool Design & MCP Integration (Domain 2, 18-20%): tool description best practices, structured error responses, tool distribution, MCP configuration, built-in tools. Hands-on lab: build a custom tool + MCP server |
| Evening | Self-directed: experiment with tools and MCP |

Wednesday — Claude Code + Agentic Architecture Part 1

|------|----------|

| Time | Activity |
| --- | --- |
| 8:00–9:00 | Breakfast + brainstorming: agentic use cases from your practice |
| 9:00–12:00 | Claude Code Configuration & Workflows (Domain 3, 20%): CLAUDE.md hierarchy, path-scoped rules, custom skills, plan mode, iterative refinement, CI/CD integration, batch processing |
| 12:00–1:00 | Lunch |
| 1:00–5:00 | Agentic Architecture & Orchestration Part 1 (Domain 1, 25-27%): agentic loops, multi-agent coordination, subagent spawning, task decomposition. Hands-on: build a multi-agent workflow |
| Evening | Self-directed: Claude Code deep practice, cert study |

Thursday — Agentic Architecture Part 2 + Advanced Features + Practice Exam

|------|----------|

| Time | Activity |
| --- | --- |
| 8:00–9:00 | Breakfast + brainstorming: reliability war stories |
| 9:00–12:00 | Agentic Architecture Part 2: session state, orchestration strategies, hooks. Context Management & Reliability (Domain 5, 15%): cross-conversation persistence, summarization risks, error propagation, escalation, provenance |
| 12:00–1:00 | Lunch |
| 1:00–3:00 | Advanced features lab: vision, PDF processing, extended thinking, prompt caching, batch API, citations |
| 3:00–5:00 | Full practice exam simulation + answer review. Individual gap analysis |
| Evening | **Team dinner.** Build project kickoff: define scope, specs, architecture |

Friday — Mock Exam + Week 1 Close

|------|----------|

| Time | Activity |
| --- | --- |
| 9:00–12:00 | Mock exam #2 + targeted review of weak domains. Cert prep strategy: participants must schedule and pass the exam within 2 weeks of course completion; exam fee reimbursed upon passing |
| 12:00–1:00 | Lunch |
| 1:00–3:00 | Week 1 retro. Prep for virtual Week 2: build project assignments, team working agreements. Travel home |

#### Week 2: AI Build Methodology (Virtual — Reusable Across All Vendors)

Monday — AI Product Process + Sprint 1

|------|----------|

| Time | Activity |
| --- | --- |
| 11:00–12:00 | Reconvene virtually. AI Product Process overview: from strategy to specs. Define product vision, user stories, success criteria using Claude |
| 12:00–1:00 | Lunch |
| 1:00–4:00 | Build Sprint 1: architecture + scaffolding. Teams define project structure, set up repos, configure CLAUDE.md and harnesses using Claude Code |
| Evening | **Virtual team dinner** (optional). Continue building |

Tuesday — Harness Design + Sprint 2

|------|----------|

| Time | Activity |
| --- | --- |
| 8:00–9:00 | Standup + brainstorming: what's working, what's blocking |
| 9:00–12:00 | Harness Design: CLAUDE.md files, skills, hooks, MCP configs for team collaboration. How to make Claude a reliable team member. Collaboration patterns across personas |
| 12:00–1:00 | Lunch |
| 1:00–5:00 | Build Sprint 2: core features. Apply harness patterns. Each persona contributes from their lens (architect designs, engineer builds, BA writes specs, PM prioritizes, data engineer pipelines, AI engineer tunes) |
| Evening | Self-directed building |

Wednesday — Testing & Evaluation + Sprint 3

|------|----------|

| Time | Activity |
| --- | --- |
| 8:00–9:00 | Standup + brainstorming: testing AI systems — what scares you? |
| 9:00–12:00 | Testing, Evaluation & Reliability: eval frameworks, prompt regression testing, quality gates, monitoring, observability for AI systems |
| 12:00–1:00 | Lunch |
| 1:00–5:00 | Build Sprint 3: integration, testing, hardening. Teams apply eval patterns to their builds. Cross-team code reviews |
| Evening | Self-directed building |

Thursday — Deployment & Communications + Sprint 4

|------|----------|

| Time | Activity |
| --- | --- |
| 8:00–9:00 | Standup + brainstorming: how do you tell the story of what you built? |
| 9:00–12:00 | Deployment & Communications: packaging for delivery, documentation, stakeholder demos, writing about what you built, internal marketing of AI capabilities |
| 12:00–1:00 | Lunch |
| 1:00–5:00 | Build Sprint 4: final polish, demo prep, write-up. Each team prepares a 15-min presentation |
| Evening | **Virtual team dinner** (optional). Final demo prep |

Friday — Demos + Program Close

|------|----------|

| Time | Activity |
| --- | --- |
| 9:00–12:00 | Team demos & presentations (all teams present to facilitators + invited leaders). Feedback and scoring |
| 12:00–1:00 | Lunch |
| 1:00–3:00 | Cohort retro, trainer selection (2-3 identified), cert study plan, India cohort planning input. Program close |

### Key Objectives

1. Build a certified bench: 12 practitioners across 6 roles pass the Claude Certified Architect exam, providing externally validated, client-facing credibility

2. Establish a repeatable process: The cohort produces the curriculum, playbooks, and trainer pipeline that enables future cohorts (starting with India) to run without additional program design investment

3. Create internal trainers: 2-3 qualified trainers who can scale the program across geographies and to client sites

### Timeline

|-------|----------|-----------|-----------|

| Phase | Duration | Activities | Milestone |
| --- | --- | --- | --- |
| Approval & Candidate Selection | Jun 4 – Jun 6 | Exec approval, charge codes, candidate identification, intro emails | Verbal approval, 12 candidates invited |
| Preparation | Jun 9 – Jun 13 | Roster finalized, API provisioning, pre-work sent, travel booked, catering, curriculum finalized, facilitator dry run | All logistics confirmed, participants prepped |
| Week 1 (NYC, in-person) | Jun 15 – Jun 19 | Anthropic technology deep dive, all 5 certification domains, labs, mock exams, build project kickoff | 5 exam domains covered, teams formed |
| Week 2 (virtual) | Jun 22 – Jun 26 | AI Build Methodology, 4 build sprints, team demos to leadership | Cohort complete, 2-3 trainers identified |
| Certification | Jun 27 – Jul 11 | Individual exam preparation; participants must schedule and pass within 2 weeks | 12 certified Claude Architects |
| Retrospective & India decision | Jul 14 | Compile results, cohort retro, decide India cohort timing | Go/no-go on India expansion |

## Budget

### Cost Summary

Total Investment: $290,525

|---|--------------|---------------|-------|

|  | People's Time | Real Expenses | Total |
| --- | --- | --- | --- |
| **Facilitators** | $60,800 | $9,925 | $70,725 |
| **Students** | $192,000 | $27,800 | $219,800 |
| **Total** | **$252,800** (87%) | **$37,725** (13%) | **$290,525** |

### People's Time — $252,800

This is not new spend. It is the billing value of time redirected from client work to internal capability building.

Facilitators — $60,800

|------|-----------|------|--------|

| Role | Commitment | Rate | Amount |
| --- | --- | --- | --- |
| PPMD | 8 hrs/week x 2 weeks (oversight) | $800/hr | $12,800 |
| Sr. Manager | Full-time, 2 weeks | $400/hr | $32,000 |
| Manager | Full-time, 2 weeks | $200/hr | $16,000 |

Students — $192,000

| | |

|---|---|

| 12 practitioners x 2 weeks x 40 hrs/week x $200/hr | $192,000 |
| --- | --- |

### Real Expenses — $37,725

This is actual out-of-pocket spend requiring budget approval.

|------|-------------|----------|-------|

| Item | Facilitators | Students | Total |
| --- | --- | --- | --- |
| Travel — flights (domestic roundtrip) | $1,500 (3 x $500) | $3,000 (6 x $500) | **$4,500** |
| Travel — hotel (5 nights x $300) | $4,500 (3 people) | $9,000 (6 people) | **$13,500** |
| API credits (labs + build projects) | $2,000 | $14,000 | **$16,000** |
| Meals (NYC, 5 days in-person) | $1,425 | $5,700 | **$7,125** |
| Exam fees (reimbursed upon passing) | — | $1,200 (12 x $100) | **$1,200** |
| Swag | $500 | $2,000 | **$2,500** |
| **Subtotal** | **$9,925** | **$34,900** | **$37,725*** |

Note: 6 of 12 students travel; 6 are local to NYC (no travel costs). All 3 facilitators travel.

### Future Phase: India Cohort (estimated)

Pending successful completion of the US cohort, an India cohort (Bangalore, 2 weeks, 12 students) is estimated at approximately $141,000, including US co-facilitator travel (business class). This would bring the combined program to approximately $430,000 and produce 24 certified architects across 2 geographies.

## Expected Outcomes

### Quantitative

12 Claude Certified Architects across 6 roles by July 11, 2026

2-3 qualified internal trainers capable of running future cohorts (starting with India) without additional program design investment

1 complete build project demonstrating end-to-end AI product delivery using the team's AI product process

1 battle-tested curriculum with playbooks, session plans, and facilitator guides ready for reuse

### Qualitative

Client credibility: When a client asks "Have your people actually built with Claude?", the answer is yes — with certification to prove it and project artifacts to show

Delivery velocity: Practitioners who have completed the immersive program can onboard to client Anthropic engagements in days rather than weeks, because they have already navigated the full product surface and built a real system

## Risk Assessment

|------|------------|--------|-----------|

| Risk | Probability | Impact | Mitigation |
| --- | --- | --- | --- |
| Participants cannot be freed from client work for 2 weeks (Jun 15-26) | Medium | High | Secure executive sponsor commitment by Jun 5; target practitioners between engagements or on bench; candidates confirm by Jun 9 |
| Certification exam pass rate below target | Low | Medium | Curriculum structured around exam domains; 80% readiness target provides margin; 2-week window to schedule and pass; exam fees only reimbursed upon passing, incentivizing preparation |
| Virtual Week 2 has lower engagement than in-person Week 1 | Medium | Medium | Build project accountability keeps teams engaged; daily standups and structured deliverables; facilitators actively monitor participation |
| Anthropic releases major platform changes during program | Low | Medium | Curriculum includes "latest developments" module; facilitators monitor announcements; modular design allows swapping individual sessions |

## Competitive Positioning

This memo does not advocate for Anthropic over other AI platforms. Our firm maintains technology-agnostic advisory relationships with clients.

However, the market is moving. Clients who select Anthropic — and an increasing number are, particularly in regulated industries — need implementation partners with demonstrated expertise. Our competitors are investing:

Boutique AI firms are building entire practices around Claude, with teams of certified architects

Large consultancies are announcing Anthropic partnerships and standing up dedicated Centers of Excellence

Anthropic's own professional services team is growing, and will increasingly compete with us for implementation work

Our investment is defensive and offensive: defensive because without it, we will lose Anthropic implementation work to competitors who have invested; offensive because the train-the-trainer model allows us to scale faster and more cost-effectively than competitors who rely on centralized training programs.

## Ask

We request approval of $290,525 to fund the Anthropic Deep Competency Program — US Cohort as described in this memo.

Specifically, we ask for:

1. Budget approval of $37,725 in real expenses (the direct out-of-pocket cost for travel, API credits, meals, exams, and swag)

2. Time commitment of $252,800 in people's time — 12 practitioners and 3 facilitators freed from client commitments for 2 weeks

3. Executive sponsorship to ensure participant availability and organizational priority

4. Decision by June 5, 2026 to maintain the program timeline — Week 1 starts June 15

The people's time investment is recouped through accelerated client delivery capability and the elimination of ongoing training program costs via the train-the-trainer model. A successful US cohort positions us to expand to India (~$141K additional) and ultimately build a global bench of 24+ certified architects.

## Expansion Roadmap

This budget approval funds the full roadmap below. Phases 2-4 do not require additional executive approval — the plan is ours to execute once funded, with phasing driven by client demand and trainer availability.

### Phase 1: Prove the Model (Q3 2026)

1 US cohort (Anthropic), 12 students, NYC

Produce 12 certified Claude Architects + 2-3 internal trainers

Output: proven curriculum, playbooks, facilitator guides, AI build methodology

$290,525 (this ask)

### Phase 2: Scale Geographically — Anthropic (Q4 2026)

GDS India cohort (Bangalore, 12 students) — Phase 1 graduates co-facilitate

1 additional US cohort (second city) — Phase 1 graduates facilitate independently

~24 additional certified Anthropic architects

India cohorts significantly cheaper ($45/hr student rate vs $200/hr)

~$280K estimated

### Phase 3: Multi-Vendor Expansion (Q1-Q2 2027)

GDS Mexico cohort (Anthropic — nearshore bench)

Launch new vendor Week 1 tracks: NVIDIA, AWS, GCP

Only Week 1 needs design per vendor; Week 2 (AI Build Methodology) reused as-is

~36+ additional certified architects across 4 technologies

~$400-500K estimated (multiple cohorts, decreasing unit cost per cohort)

### Phase 4: Full Portfolio (Q3 2027+)

Add OpenAI, IBM, Palantir, Databricks, and others as client demand dictates

Running across all geographies (US multi-city, GDS India, GDS Mexico)

150+ total certified architects across 8+ technology platforms

Fully self-sustaining — trainer pool runs without central program team

Unit cost drops to ~$50-80K per cohort (no methodology design, internal facilitators, GDS cost rates)

### Technology Portfolio

The program is architected for multi-vendor reuse. This is a critical strategic advantage: we are not building an Anthropic training program — we are building a technology enablement engine that works across any AI platform.

Week 1 is vendor-specific — rebuilt per technology to cover that vendor's products, APIs, architecture patterns, and certification domains

Week 2 (AI Build Methodology) is vendor-agnostic — reusable as-is across all technologies. Specs, harnesses, collaboration patterns, testing, deployment, and communications apply regardless of the underlying AI platform

Each new vendor program requires approximately half the design effort of this initial investment

|--------|-------------|---------------|

| Vendor | Week 1 Focus | Certification |
| --- | --- | --- |
| **Anthropic** (this cohort) | Claude API, Claude Code, Agent SDK, MCP | Claude Certified Architect |
| **NVIDIA** | NIM microservices, GPU infrastructure, inference optimization, CUDA | NVIDIA Certified AI Solutions Architect |
| **AWS** | Bedrock, SageMaker, multi-model orchestration, Lambda AI | AWS Machine Learning Specialty |
| **Google Cloud** | Gemini, Vertex AI, AI Studio, Search grounding | Google Cloud Professional ML Engineer |
| **OpenAI** | GPT models, Assistants API, function calling, GPTs | OpenAI certifications (as available) |
| **IBM** | watsonx, Granite models, AI governance, OpenPages | IBM AI Engineering Professional |
| **Palantir** | Foundry, AIP, ontology-driven AI, pipeline orchestration | Palantir Foundry certification |
| **Databricks** | Mosaic ML, Model Serving, lakehouse AI, MLflow | Databricks ML Professional |
| **Others** | As client demand dictates | Vendor-specific |

The train-the-trainer model compounds across technologies: a facilitator who has run the Anthropic cohort can run the AWS cohort with only Week 1 retraining, because Week 2 methodology skills transfer directly.

### Geographic Reach

|-----------|-------------------|-----------------|

| Geography | Cohort Cost Profile | Strategic Value |
| --- | --- | --- |
| **US (multi-city)** | ~$290K per cohort (at onshore rates) | Client-facing delivery bench, trainer pipeline |
| **GDS India** | ~$141K per cohort (lower labor rates, higher travel) | Cost-efficient scale, 24/7 delivery capability |
| **GDS Mexico** | ~$120K per cohort (lower labor, lower travel than India) | Nearshore bench, US time zone alignment |

### Cumulative Scale

|-------|----------|---------|-------------|-------------|---------------------|-------------|

| Phase | Timeline | Cohorts | Technologies | Geographies | Certified Architects | Facilitators |
| --- | --- | --- | --- | --- | --- | --- |
| Phase 1 | Q3 2026 | 1 | 1 (Anthropic) | 1 (US) | 12 | 3 (program team) |
| Phase 2 | Q4 2026 | 3 | 1 (Anthropic) | 2 (US, India) | 36 | 5-6 (Phase 1 grads) |
| Phase 3 | Q1-Q2 2027 | 7+ | 4 (+ NVIDIA, AWS, GCP) | 3 (+ Mexico) | 72+ | 10+ (Phase 1-2 grads) |
| Phase 4 | Q3 2027+ | 12+ | 8+ (+ OpenAI, IBM, Palantir, Databricks) | 3+ | 150+ | Self-sustaining pool |

## Appendix

### Vendor Overview

Anthropic (founded 2021, San Francisco) is an AI safety company building frontier AI systems. Their Claude model family includes:

|-------|------|---------------|----------|

| Model | Tier | Context Window | Best For |
| --- | --- | --- | --- |
| Claude Opus 4.6 | Flagship | 1M tokens | Deep reasoning, complex analysis, coding |
| Claude Sonnet 4.6 | Balanced | 200K tokens | Speed/quality balance, general tasks |
| Claude Haiku 4.5 | Fast | 200K tokens | High throughput, cost efficiency |

Key platform capabilities: Messages API, tool use/function calling, vision, PDF processing, extended thinking, streaming, batch processing, prompt caching, citations, Claude Code (agentic CLI), Agent SDK.

Cloud availability: Amazon Bedrock, Google Cloud Vertex AI.

Enterprise posture: SOC 2 compliant, HIPAA eligible, enterprise SLAs available.

### References

Anthropic Developer Documentation: docs.anthropic.com

Anthropic Cookbook: github.com/anthropics/anthropic-cookbook

Anthropic Courses: github.com/anthropics/courses

Claude Certified Architect Program: anthropic.com/certifications

Generated by Forge — Anthropic Enablement Program 2026